## Project Plan
Sprint | Dates | Goals / Milestones | Key Deliverables
Sprint 1 | 01-Oct-2025 – 14-Oct-2025 | Setup & initial development | API contracts, basic UI
Sprint 2 | 15-Oct-2025 – 28-Oct-2025 | Core functionality | Feature A, Feature B
Sprint 3 | 29-Oct-2025 – 11-Nov-2025 | UAT-ready build, deploy to UAT | Full integration, UAT deployment
Sprint 4 | 12-Nov-2025 – 25-Nov-2025 | UAT execution & Production deployment | UAT fixes, Prod deployment

## Dependencies
Dependency | Owner Team | Needed By Sprint | Status | Comments
APIs (Auth, Payment) | API Team | Sprint 2 | Pending | Must be delivered by Oct 20
UI Screens | Design Team | Sprint 1 | In Progress | Wireframes ready, dev UI needed
Test Data | QA Team | Sprint 3 | Not Started | Required for UAT execution

## User Stories
Sprint | User Story ID | Description | Acceptance Criteria | Owner | Status
Sprint 1 | US-01 | As a user, I can log in | Login with valid creds, error on invalid | Dev1 | Planned
Sprint 1 | US-02 | As a user, I can view dashboard | Dashboard loads with data from API | Dev2 | Planned
Sprint 2 | US-03 | As a user, I can make payment | Payment API integration, confirmation | Dev3 | Planned
Sprint 2 | US-04 | As a user, I can view transaction history | Transactions retrieved and displayed | Dev1 | Planned
Sprint 3 | US-05 | As a user, I can use system in UAT | End-to-end flow validated in UAT | QA | Planned
Sprint 4 | US-06 | As a user, I get production-ready system | Deployment to Prod successful | Release Manager | Planned